## Execution Timeline
| 2021-02-03 | 2021-02-10 | 2021-02-17 | 2021-02-24 | 2021-03-03 | 2021-03-10 | 2021-03-17 | 2021-03-24 | 2021-03-31 | 2021-04-07 | 2021-04-14 | 2021-04-21 | 2021-04-28
Status update 1 | bar: 2021-02-03
Troubleshoot Electrostatic Brakes | bar: 2021-02-03
Explore alternative for haptic feedback | 2021-04-21: Not Started
Status update 2 | 2021-04-21: In Progress
Test motors with microcontroller | 2021-04-21: Completed
Single Finger integration | 2021-04-21: Behind Schedule
Fabricate flex sensors for entire hand | bar: 2021-02-24 to 2021-03-03
Status update 3 | bar: 2021-03-03
Multi-finger integration | bar: 2021-03-03 to 2021-03-10
Root cause analysis of electrostatics | bar: 2021-04-14 to 2021-04-28
Status update 4 | bar: 2021-03-17
System validation | bar: 2021-03-17 to 2021-03-31
Status Update 5 | bar: 2021-03-31
Final Presentation
Final System Demo
Final Report

## Validation Plan
System | Paragraph # | Test Name | Success Criteria | Methodology | Status | Engineer
| 3.2.1.1 | Haptic Feedback | 10 points of feedback experienced | turn on all 10 vibe motors attached to worn glove | ONGOING | Ben
| 3.2.1.2 | Finger Tracking | Calculated joint rotation within 5 degrees of actual | With protactor alligned to each joint, bend to 45 and 90 degrees | ONGOING | Nick
| 3.2.1.3 | GUI Classification | Intensity of feedback classified as none, soft, or hard | Run GUI in standby, then interact with soft, and hard object | TESTED | Nick
| 3.2.2.1 | Mass of Glove | Mass of glove, motors, and sensors under 170g | Weigh assembled glove on digital scale | UNTESTED | Team
| 3.2.3.2 | Variable Feedback | Sense maximum vibration for hard object and half of max vibration for soft objects | Interact with soft object and hard object while wearing assembled glove | UNTESTED | Team
|  | System Demo | Fluently demonstarte all above tests | operate glove in virtual enviroment as an end user | UNTESTED | Team
Remaining Subsytem | Subsystem | Test Name | What Needs to Happen | Status | Date Needed | Engineer
| GUI | Hand Rendered | GUI displays hand structure to user | Hand structure completed, but hand not visible | 2021-03-24 | Nick
| Motors | Vibration | Vibrate motors while coneced to control circuit | COMPLETE | 2021-03-08 | Ben
| Motors | MCU Control | Control Vibration motors with MCU | COMPLETE | 2021-03-08 | Ben
| GUI/Motors | Verify Comms | Control MCU with outputs from GUI | ONGOING, rudimentary test complete, but still need to verify accuracy | 2021-03-09 | Team